## Slide 1: HR Project ID Card template
February 2025

## Slide 2: Competencies volunteering - Platform “J’agis”
PROJECT ID CARD
HUMAN RESOURCES
Sponsor : N/A
4.1 Project Cost (total expected)
4.2 Run costs impacts (yearly)
1.1 Problem Opportunity
5 – Planning and organization
1 - The Why of the project
2 - Tangible Results and closure criteria
Offer CACEIS employees a charities platform. The aim is to connect employees with associations and give them the possibility to realize missions for the civil society. 5 skills sponsorship days are offered.
2.1 Project tangible results
2.3 Project closure criteria
7 - Horizon project?
5.2 Business/IT Team leaders
Who are the business and IT Leads for the project
HR Lead: Alexandra Causi
IT Lead: N/A
5.3 Other key contributors
To launch J’agis: 11,2 k€ HT
6 - Project category
3 - Project scope
Regulatory
Business Development
Client
Internal/Productivity
CSR/ HR : engagement
IT Run cost (MD / K€): 11,2 k€ HT
5.1 Duration
1.2 Main Value Axis
(cf. Appendix)
People engagement
Start Date: end of April 2025
End Date: end December 2025
Yes
No
2.2 Tangible results in the next 3 months
Scope 2025: Pilot in France
before international extension (waiting for the GO from the EXCO CAsa : summer 2025)
Acquisition rate: number of opened accounts
Engagement rate: number of missions subscriptions
A representative number of employees who:
registered on the platform
Signed up for missions
Realized missions
Number of missions and traffic on the platform will be analysed before extending J’Agis to International entities
8 - Compliance topics checked?
Yes
No
9 – Data Privacy implication?
Yes
No
Internal: /
External: Crédit Agricole S.A. (Team “mécénat”) + Wenabi

## Slide 3: Competencies volunteering - Platform “J’agis”
Project Status Report as of 16/01/2026
Achievements / What has been done
Next steps
Risks / Difficulties encountered
Decision to be taken
Project scope/Opportunity
Offer CACEIS employees a charities platform.
The aim is to connect employees with associations and give them the possibility to realize missions for the civil society. 5 skills sponsorship days are offered.
SSO access: OK + DPO & CISO validation: OK + Signature of contract: end of June
French MD presentation: 12/03 French Managing Committee presentation: 8/04 / French WC presentation: 11/04.
Kick off of the platform: 29/04 - Communications, interventions, testimonies, animations,…
Presentation to the HR international Dev Co in the aim of international extension (12 Sep) => answers are still expected
Presentation to the Sustainability Center (29 sep)
Webinar (26 Sep)
Diversity Month (nov): Pushing missions following themes: gender balance, social diversity, disability, intergenerational
Number of opened accounts: 341 employees activated accounts (of 1800 permanent contracts) => Acquisition rate: 18,9% / Satisfaction rate: 4.9/5
Number of assignments subscriptions: 71
Number of assignments: 48 realised by 34 employees => Engagement rate*: 1,88%
16 challenges realized
Contribution to the International Volunteer Day and presentation of J’agis (8/12)
Solidarity team building (risks department team) in a forest
Go on following the rate of global engagement:
  Acquisition rate: number of opened accounts
  Engagement rate: number of missions realised
Go on organising webinars to strengthen visibility of J’agis
Define 2026 roadmap
Collect entities answers on the decision to roll out or not “WE ACT”
R
A
Sponsor : NA
IT PM : not required
Project committee : NA
Planned :
Burnt :
G
0%
25%
75%
50%
100%
Difficulties to onboard employees on the program
Costs and human resources needed to deploy in entities
NO GO from CACEIS entities to accept to roll out the program
*ratio of employees who completed an assignment / total number of employees concerned over the year
GO / NO GO from entities

## Slide 4: Appendix

## Slide 5: Competencies volunteering - Platform “J’agis”
Project Status Report as of 20/06/2025
Achievements / What has been done
Next steps
Risks / Difficulties encountered
Decision to be taken
Project scope/Opportunity
Offer CACEIS employees a charities platform.
The aim is to connect employees with associations and give them the possibility to realize missions for the civil society. 5 skills sponsorship days are offered.
SSO access: OK
DPO & CISO validation: OK
French MD presentation: 03/12
French Managing Committee presentation: 04/08
French works council presentation: 04/11
Plan communication
Prepare communications, interventions, testimonies, animations,…
Number of opened accounts: 125
Number of missions subscriptions: 14
Signature of contract: end June
Follow the rate of global engagement:
  Acquisition rate: number of opened accounts
  Engagement rate: number of missions subscriptions
Organise webinars to strengthen visibility of J’agis (Sep.)
Present the program in the Sustainability Center (sep.?)
R
A
Sponsor : NA
IT PM : not required
Project committee : NA
Planned :
Burnt :
G
0%
25%
75%
50%
100%
No GO from Crédit Agricole S.A. Exco for an international extension
Difficulties to onboard employees on the program

## Slide 6: Competencies volunteering - Platform “J’agis”
Project Status Report as of 31/08/2025
Achievements / What has been done
Next steps
Risks / Difficulties encountered
Decision to be taken
Project scope/Opportunity
Offer CACEIS employees a charities platform.
The aim is to connect employees with associations and give them the possibility to realize missions for the civil society. 5 skills sponsorship days are offered.
SSO access: OK
DPO & CISO validation: OK
French MD presentation: 03/12
French Managing Committee presentation: 04/08
French works council presentation: 04/11
Communications, interventions, testimonies, animations,…
Signature of contract: end of June
Number of opened accounts: 241 employees activated accounts (of 1800 permanent contracts) => Acquisition rate: 13,4%
Number of assignments subscriptions: 28
Number of assignments: 12 realised by 11 employees => Engagement rate*: 0,6%
Go on following the rate of global engagement:
  Acquisition rate: number of opened accounts
  Engagement rate: number of missions realised
Organise webinars to strengthen visibility of J’agis (Sep.)
Present the program to the HR international Dev Co in the aim of international extension (12th Sep)
Present the program in the Sustainability Center (sep.)
R
A
Sponsor : NA
IT PM : not required
Project committee : NA
Planned :
Burnt :
G
0%
25%
75%
50%
100%
No GO from Crédit Agricole S.A. Exco for an international extension
Difficulties to onboard employees on the program
NO GO from CACEIS entities to accept to roll out the program
*ratio of employees who completed an assignment / total number of employees concerned over the year
GO / NO GO (or later GO) from entities

## Slide 7: Competencies volunteering - Platform “J’agis”
Project Status Report as of 30/09/2025
Achievements / What has been done
Next steps
Risks / Difficulties encountered
Decision to be taken
Project scope/Opportunity
Offer CACEIS employees a charities platform.
The aim is to connect employees with associations and give them the possibility to realize missions for the civil society. 5 skills sponsorship days are offered.
SSO access: OK + DPO & CISO validation: OK + Signature of contract: end of June
French MD presentation: 03/12 / French Managing Committee presentation: 04/08 / French WC presentation: 04/11
Communications, interventions, testimonies, animations,…
Number of opened accounts: 272 employees activated accounts (of 1800 permanent contracts) => Acquisition rate: 15,1%
Number of assignments subscriptions: 30
Number of assignments: 14 realised by 12 employees => Engagement rate*: 0,66%
15 challenges realized
Satisfaction rate: 4.8/5
Presentation to the HR international Dev Co in the aim of international extension (12th Sep) => answers are expected
Presentation to the Sustainability Center (29th sep)
Webinar(26th Sep)
Go on following the rate of global engagement:
  Acquisition rate: number of opened accounts
  Engagement rate: number of missions realised
Go on organising webinars to strengthen visibility of J’agis (nov/dec)
Diversity Month (nov): Pushing missions following themes: gender balance, social diversity, disability, intergenerational
Collect entities answers on the decision to roll out or not “WE ACT”
Contribute to the ambassadors celebration and highlight J’agis (12/05)
R
A
Sponsor : NA
IT PM : not required
Project committee : NA
Planned :
Burnt :
G
0%
25%
75%
50%
100%
No GO from Crédit Agricole S.A. Exco for an international extension
Difficulties to onboard employees on the program
NO GO from CACEIS entities to accept to roll out the program
*ratio of employees who completed an assignment / total number of employees concerned over the year
GO / NO GO (or later GO) from entities

## Slide 8: Competencies volunteering - Platform “J’agis”
Project Status Report as of 2/12/2025
Achievements / What has been done
Next steps
Risks / Difficulties encountered
Decision to be taken
Project scope/Opportunity
Offer CACEIS employees a charities platform.
The aim is to connect employees with associations and give them the possibility to realize missions for the civil society. 5 skills sponsorship days are offered.
SSO access: OK + DPO & CISO validation: OK + Signature of contract: end of June
French MD presentation: 12/03 French Managing Committee presentation: 8/04 / French WC presentation: 11/04.
Kick off of the platform: 29/04 - Communications, interventions, testimonies, animations,…
Presentation to the HR international Dev Co in the aim of international extension (12 Sep) => answers are still expected
Presentation to the Sustainability Center (29 sep)
Webinar (26 Sep)
Diversity Month (nov): Pushing missions following themes: gender balance, social diversity, disability, intergenerational
Number of opened accounts: 319 employees activated accounts (of 1800 permanent contracts) => Acquisition rate: 17,7%
Number of assignments subscriptions: 68
Number of assignments: 37 realised by 31 employees => Engagement rate*: 1,72%
16 challenges realized
Satisfaction rate: 4.9/5
Go on following the rate of global engagement:
  Acquisition rate: number of opened accounts
  Engagement rate: number of missions realised
Go on organising webinars to strengthen visibility of J’agis (4 dec)
Contribute to organize the International Volunteer Day and highlight J’agis (8/12)
Define 2026 roadmap
Collect entities answers on the decision to roll out or not “WE ACT”
R
A
Sponsor : NA
IT PM : not required
Project committee : NA
Planned :
Burnt :
G
0%
25%
75%
50%
100%
Difficulties to onboard employees on the program
NO GO from CACEIS entities to accept to roll out the program
*ratio of employees who completed an assignment / total number of employees concerned over the year
GO / NO GO from entities